## Tool Stack
LEADFLOW AI V2 — TOOL STACK & ARCHITECTURE (Polsia-Augmented)
De Villiers (Lead) ¦ Marinus (Collaborator) ¦ JigsawAI Initiative ¦ V2: Outcome-Based Positioning
A. COMPLETE TOOL STACK — All accounts independently owned and controlled
# | Tool | Category | Monthly Cost | What It Does | Why Independent | Polsia Interaction
CORE INFRASTRUCTURE — Owned by De Villiers, Zero Polsia Dependency
1 | Instantly.ai | Email Sending | $97-$176 | High-volume cold email with automated warmup, rotation across mailboxes, deliverability monitoring, bounce management. 500-2,000 emails/day. | YOUR account = YOUR sending reputation. Polsia outage = emails still send. | Polsia drafts sequences → De Villiers approves → loaded into Instantly.
2 | Apollo.io | Data Enrichment | $99 (Pro) | 275M+ contacts, verified emails, job titles, company data, intent signals. Builds targeted prospect lists per ICP. | YOUR data = YOUR prospect lists. Export all enriched data. No platform lock-in. | Polsia generates ICP criteria → De Villiers runs Apollo search → exports CSV.
3 | HubSpot CRM | CRM & Pipeline | $0-$50 | Central system of record for all clients, pipeline, deal stages, contact history, reporting. | YOUR CRM = YOUR client relationships. Independent of all execution tools. | Manual sync: metrics from Instantly/LinkedIn into HubSpot weekly. Polsia generates summaries.
4 | Stripe (YOUR account) | Billing | 2.9% + $0.30/tx | YOUR OWN Stripe account for client billing. Recurring subscriptions, invoicing, payment tracking. | YOUR billing = YOUR revenue. 0% Polsia revenue share. Full margin control. | NO Polsia involvement in billing. Completely independent.
5 | Namecheap/Cloudflare | Domains & DNS | $12-$15/domain | Domain registration, DNS management for 8+ sending domains, main website, client subdomains. | YOUR domains = YOUR infrastructure. Transferable, renewable, fully controlled. | None. Fully independent.
6 | Carrd / Framer | Website | $0-$19/mo | Landing page for LeadFlow AI with V2 guarantee messaging, pricing, case studies, lead capture. | YOUR website = YOUR brand presence. Guarantee narrative owned by you. | Polsia drafts copy → De Villiers approves → implemented independently.
AI EXECUTION LAYER — Polsia as Co-Pilot (NOT Infrastructure)
7 | Polsia | AI Execution | $49/mo | Autonomous AI agent running nightly cycles. Drafts email sequences, ICP criteria, blog content, campaign analysis, optimisation suggestions. | AI BRAIN, not infrastructure. All outputs reviewed by De Villiers before client deployment. Polsia disappears = lose convenience, not capability. | CORE ROLE: Strategy & content drafting. ALL output through De Villiers approval gate before touching any client prospect.
CHANNEL-SPECIFIC & SUPPORT TOOLS
8 | Expandi / Dripify | LinkedIn | $99/mo | Automated LinkedIn connection requests, messaging sequences, profile visits, content engagement. Cloud-based, 24/7. | YOUR LinkedIn automation = YOUR network growth. Independent. | Polsia drafts LinkedIn templates → De Villiers approves → loaded into Expandi.
9 | Meta / Google Ads | Paid Advertising | Variable | Facebook, Instagram, Google advertising for client campaigns and LeadFlow client acquisition. | YOUR ad accounts = YOUR audience data, pixel data, custom audiences. | Polsia suggests targeting + copy → De Villiers creates/manages campaigns.
10 | Notion | Knowledge Base | $0 | Stores all vertical playbooks, email templates, ICP definitions, process docs, client SOPs. The real IP of the business. | YOUR playbooks = YOUR intellectual property. Platform-independent. | Polsia outputs stored here. Playbooks live in Notion, not inside Polsia.
11 | Calendly | Scheduling | $0 (Free) | Booking link for discovery calls and client meetings. Embedded in email signatures, website, LinkedIn. | YOUR calendar = YOUR pipeline. Direct booking without intermediary. | De Villiers Calendly link included in approved outreach sequences.
12 | Google Analytics | Web Analytics | $0-$9/mo | Website traffic, conversion tracking, source attribution. | YOUR analytics = YOUR performance data. | Polsia can read analytics to inform content strategy.
13 | Loom | Video & Comms | $0 (Free) | Screen recording for onboarding tutorials, campaign walkthroughs, prospect-facing video messages. | Adds personal touch. Human differentiator vs pure-AI competitors. | None. Human-only tool.
MONTHLY TOOL COST SUMMARY
Core infrastructure (Instantly + Apollo + HubSpot + domains) | [5 empty] | $260-$340/mo
AI execution (Polsia) | [5 empty] | $49/mo
Channel tools (Expandi + Calendly) | [5 empty] | $99/mo
Website + Analytics | [5 empty] | $0-$28/mo
TOTAL FIXED TOOL COSTS | [5 empty] | $408-$516/mo
Per-client variable (additional Instantly mailboxes) | [5 empty] | ~$30-$50/client
B. PROCESS FLOWS — How Information Moves Between Tools (V2)
FLOW 1: NEW CLIENT ONBOARDING (V2 — Guarantee Tier Confirmed)
Step | Activity | From (Source) | To (Destination) | Detail | Human Gate? | De Villiers Action
Step 1 | Client signs contract + pays | Stripe (YOUR account) | Calendly | Client completes payment via YOUR Stripe. Onboarding call booked via Calendly link. | No | Confirm payment, send welcome email.
Step 2 | ICP intake questionnaire | Google Forms | Notion | Client completes ICP questionnaire. Responses stored in client Notion folder. | No | Share form link, review responses.
Step 3 | Polsia generates campaign strategy | Notion (ICP data) | Polsia | Paste ICP data into Polsia. AI generates: target criteria, 5-touch sequences, LinkedIn msgs, ad angles. | No | Feed ICP data to Polsia.
Step 4 | HUMAN APPROVAL GATE | Polsia output | De Villiers review | Review ALL Polsia output. Edit sequences for tone, accuracy, compliance, V2 guarantee alignment. | YES | Approve or revise. NOTHING touches client prospects without sign-off.
Step 5 | Build prospect list | Apollo.io | CSV export | Using approved ICP criteria, run Apollo search. Export verified prospect list. | No | Run Apollo search, export, verify quality.
Step 6 | Load into sending tools | Apollo CSV | Instantly + Expandi | Upload list to Instantly (email) and Expandi (LinkedIn). Load approved sequences. Set volume limits. | No | Configure campaigns, set sending schedule.
Step 7 | Campaign goes live | Instantly + Expandi | HubSpot | Campaigns begin. Key metrics flow to HubSpot. Client notified of launch + guarantee terms confirmed. | No | Notify client, confirm guarantee tier.
FLOW 2: DAILY CAMPAIGN EXECUTION
Step | Activity | From (Source) | To (Destination) | Detail | Human Gate? | De Villiers Action
Step 1 | Instantly sends email batches | Instantly | Prospect inboxes | Automated: 50-75 emails per mailbox/day. Warmup continues in background. | No | Monitor deliverability dashboard daily.
Step 2 | Expandi runs LinkedIn sequences | Expandi | LinkedIn | Automated: connection requests, follow-up messages, profile visits per schedule. | No | Check acceptance rates weekly.
Step 3 | Replies flow into Instantly inbox | Prospect replies | Instantly | Positive, negative, OOO replies captured in unified inbox. | No | Triage daily (or VA from Month 4).
Step 4 | HUMAN APPROVAL GATE — Positive replies | Instantly inbox | De Villiers | Positive replies require human response. Polsia drafts reply; De Villiers personalises and sends. | YES | Personalise and send Polsia-drafted replies.
Step 5 | Polsia nightly analysis | Campaign data | Polsia | AI evaluates open rates, reply rates, bounce rates. Flags underperformers. Suggests A/B tests. | No | Review Polsia analysis each morning.
Step 6 | HUMAN APPROVAL GATE — Optimisations | Polsia suggestions | De Villiers | Review suggested changes. Implement approved changes in Instantly/Expandi. Reject unsuitable suggestions. | YES | Approve or reject each optimisation suggestion.

## Implementation Plan
LEADFLOW AI V2 — 12-MONTH IMPLEMENTATION PLAN
De Villiers (Lead Owner) ¦ Marinus (Strategy Collaborator) ¦ JigsawAI Initiative ¦ V2: Outcome-Based Positioning
# | Task / Activity | Owner | Phase | Status | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
PHASE 1: FOUNDATION — Build Independent Infrastructure & V2 Positioning (Weeks 1-8)
1 | Purchase 8 sending domains (Namecheap/Cloudflare) | De Villiers | Phase 1 | Not Started | Critical path — start Day 1
2 | Set up YOUR Stripe account (independent billing, 0% Polsia share) | De Villiers | Phase 1 | Not Started | Own your revenue
3 | Create Instantly.ai account (3 initial mailboxes) | De Villiers | Phase 1 | Not Started
4 | Begin domain warming in Instantly (14-day critical path) | Instantly (auto) | Phase 1 | Not Started | Must complete before first outreach
5 | Set up Apollo.io Pro plan (your own account) | De Villiers | Phase 1 | Not Started
6 | Configure HubSpot CRM (free tier, pipeline stages) | De Villiers | Phase 1 | Not Started
7 | Set up Calendly booking links | De Villiers | Phase 1 | Not Started
8 | Set up Notion workspace (playbooks, SOPs, client folders) | De Villiers | Phase 1 | Not Started | YOUR IP storage — not Polsia
9 | Create Polsia instance (AI co-pilot, NOT infrastructure) | De Villiers | Phase 1 | Not Started | Polsia = drafts only; De Villiers approves all output
10 | Build website/landing page with V2 guarantee messaging | De Villiers | Phase 1 | Not Started | Lead with guarantee, not AI features
11 | Define ICP + guarantee levels: Vertical 1 (Management Consulting) | De Villiers | Phase 1 | Not Started | Collaborate with Marinus on strategy
12 | Define ICP + guarantee levels: Vertical 2 (IT Services / MSPs) | De Villiers | Phase 1 | Not Started
13 | Define ICP + guarantee levels: Vertical 3 (SaaS Companies) | De Villiers | Phase 1 | Not Started
14 | Polsia drafts email sequences (5-touch x 3 verticals, V2 tone) | Polsia | Phase 1 | Not Started | Guarantee-led messaging
15 | APPROVAL GATE: De Villiers reviews & refines all email sequences | De Villiers | Phase 1 | Not Started | Nothing deploys without sign-off
16 | Polsia drafts LinkedIn messaging templates (V2 outcome framing) | Polsia | Phase 1 | Not Started
17 | APPROVAL GATE: De Villiers reviews & refines LinkedIn templates | De Villiers | Phase 1 | Not Started
18 | Build prospect lists in Apollo (500+ per vertical, ICP validated) | De Villiers | Phase 1 | Not Started
19 | Load approved sequences + lists into Instantly | De Villiers | Phase 1 | Not Started
20 | Domain warming VALIDATED (>90% inbox placement) | De Villiers | Phase 1 | Not Started | Do not send live outreach until validated
21 | Set up Expandi for LinkedIn automation | De Villiers | Phase 1 | Not Started
22 | Activate JigsawAI/inlumiSA network (personal outreach to 50-100 contacts) | De Villiers | Phase 1 | Not Started | Lowest CAC channel — activate first
23 | Create client onboarding questionnaire (Google Forms) | De Villiers | Phase 1 | Not Started | ICP + guarantee tier confirmation
24 | Create weekly reporting template (includes guarantee tracking) | De Villiers | Phase 1 | Not Started
25 | Store all playbooks + V2 guarantee framework in Notion (YOUR IP) | De Villiers | Phase 1 | Not Started | Portable, version-controlled
26 | Polsia generates 3 blog posts (SEO/GEO, V2 positioning) | Polsia | Phase 1 | Not Started
27 | APPROVAL GATE: De Villiers reviews & publishes blog content | De Villiers | Phase 1 | Not Started
28 | Launch own outbound for client acquisition (post-warming) | Instantly (auto) | Phase 1 | Not Started | V2 guarantee messaging in own sequences
29 | MILESTONE: First 5 paying clients signed | De Villiers | Phase 1 | Not Started | Target: end of Week 8
PHASE 2: TRACTION — Prove the V2 Guarantee Model (Weeks 9-16)
30 | Launch V2 campaigns for first 5 clients (Instantly + Expandi) | De Villiers | Phase 2 | Not Started
31 | APPROVAL GATE: Review each client campaign before launch | De Villiers | Phase 2 | Not Started | Non-negotiable — first campaigns for each client
32 | Daily response triage (Instantly + LinkedIn unified inbox) | De Villiers | Phase 2 | Not Started | VA takes over from Month 4
33 | Polsia nightly campaign analysis + optimisation suggestions | Polsia | Phase 2 | Not Started
34 | APPROVAL GATE: De Villiers reviews Polsia optimisation suggestions weekly | De Villiers | Phase 2 | Not Started | Every week — implement approved changes only
35 | A/B test sequences (implement in Instantly, not Polsia) | De Villiers | Phase 2 | Not Started
36 | Publish 2 blog posts/week (Polsia drafts, De Villiers approves) | De Villiers + Polsia | Phase 2 | Not Started
37 | Daily LinkedIn thought leadership (personal account) | De Villiers | Phase 2 | Not Started | Build personal brand as guarantee-led growth expert
38 | Build first 2 case studies from pilot clients (metrics-led) | De Villiers | Phase 2 | Not Started | Include guarantee delivery stats
39 | Create lead magnets (ICP Template, AI Playbook, Guarantee Calculator) | De Villiers + Polsia | Phase 2 | Not Started | Guarantee Calculator is new V2 asset
40 | Launch referral programme (20% commission, 3 months) | De Villiers | Phase 2 | Not Started | Activate after first case study published
41 | Track guarantee delivery per client (is guarantee being met?) | De Villiers | Phase 2 | Not Started | Early warning system — adjust before clients notice
42 | MILESTONE: 12 active clients (break-even), first guarantee validated | De Villiers | Phase 2 | Not Started | Target: end of Week 16
PHASE 3: GROWTH — Scale the Model (Weeks 17-32)
43 | Hire Part-time VA (client comms, report distribution, triage) | De Villiers | Phase 3 | Not Started | Brief Marinus on VA selection criteria
44 | Train VA on Instantly, HubSpot, reporting workflows | De Villiers | Phase 3 | Not Started
45 | VA takes over: response triage, report delivery, CRM hygiene | VA | Phase 3 | Not Started
46 | Launch Growth tier ($4,000/mo, 12 meetings guaranteed) | De Villiers | Phase 3 | Not Started | Upgrade eligible Launch clients
47 | Introduce ad management service (15% markup) | De Villiers | Phase 3 | Not Started
48 | Expand to 4th vertical (Financial Services or Professional Services) | De Villiers | Phase 3 | Not Started | Collaborate with Marinus on ICP design
49 | Polsia generates vertical 4 playbook | Polsia | Phase 3 | Not Started
50 | APPROVAL GATE: De Villiers reviews vertical 4 playbook | De Villiers | Phase 3 | Not Started
51 | Build agency partner channel (web design, CRM consultants) | De Villiers | Phase 3 | Not Started | 10% ongoing revenue share
52 | Monthly strategy review with Marinus (pipeline, guarantee rates, ICP) | De Villiers + Marinus | Phase 3 | Not Started | Monthly cadence
53 | MILESTONE: 20 active clients, $60K+ MRR | De Villiers | Phase 3 | Not Started | Target: end of Week 32
PHASE 4: SCALE — Optimise and Systematise (Weeks 33-52)
54 | Launch Enterprise tier ($6,000/mo, 18 meetings, dedicated mgr) | De Villiers | Phase 4 | Not Started
55 | Hire commission-based BD person (close new clients) | De Villiers | Phase 4 | Not Started | $2,000 base + 10% of first 3 months/client
56 | Introduce CRM integration add-on ($500/month) | De Villiers | Phase 4 | Not Started
57 | Expand to 5th and 6th verticals | De Villiers | Phase 4 | Not Started | Collaborate with Marinus on strategy
58 | Quarterly business review with Marinus (portfolio health) | De Villiers + Marinus | Phase 4 | Not Started | Strategic direction for Year 2
59 | Optimise guarantee delivery rates (target: <5% payout months) | De Villiers | Phase 4 | Not Started | Monitor per-client, per-vertical
60 | Build proprietary benchmark database (cross-client performance) | De Villiers | Phase 4 | Not Started | This is the compound moat
61 | MILESTONE: 27 active clients, $80K+ MRR, 88%+ retention | De Villiers | Phase 4 | Not Started | Target: end of Week 52

## Budget Model
LEADFLOW AI V2 — BUDGET MODEL (Polsia-Augmented ¦ Independent Stripe ¦ No Revenue Share)
Blue = inputs (change these) ¦ Black = formulas ¦ De Villiers (Lead) ¦ Marinus (Collaborator) ¦ Base Case ¦ See Scenarios tab for Conservative/Aggressive
| Month 0 (Setup) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | TOTAL
STARTUP INVESTMENT (ONE-TIME) — Month 0
Domain purchases (8 sending + 1 primary) | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Instantly.ai setup (first month) | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Apollo.io setup (first month) | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brand assets (logo, templates, V2 guarantee materials) | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Website / landing page (V2 guarantee messaging) | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legal (T&Cs, guarantee terms, privacy policy) | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Startup Investment
MONTHLY OPERATING COSTS (V2 — Independent Infrastructure)
Active Clients (assumption — change these blue numbers) | 0 | 2 | 4 | 6 | 8 | 12 | 15 | 18 | 20 | 23 | 25 | 28 | 27
Instantly.ai (base $97 + $30/extra mailbox per client) | 97
Apollo.io (Pro plan, fixed) | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
HubSpot CRM | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Polsia (AI co-pilot — single instance) | 0 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49
Expandi / Dripify (LinkedIn) | 0 | 0 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
Website + Analytics | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Own client acquisition outbound spend | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3000 | 3500 | 3500 | 4000 | 4000 | 4500 | 5000
Paid advertising (Google/Meta) | 0 | 0 | 0 | 500 | 1000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Content creation / freelancers | 0 | 500 | 500 | 500 | 750 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
Virtual Assistant(s) | 0 | 0 | 0 | 0 | 800 | 800 | 1000 | 1000 | 1200 | 2400 | 2400 | 2400 | 2400
Commission-based BD person | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000
Guarantee payouts (est. 7% of months, avg $2,500 payout) | 0
Miscellaneous / buffer | 200 | 300 | 300 | 400 | 400 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
Total Monthly Operating Costs
REVENUE (100% retained — $0 Polsia revenue share ¦ YOUR Stripe account)
Average retainer per client ($ — change blue numbers) | 0 | 0 | 2500 | 2700 | 2800 | 3000 | 3000 | 3100 | 3200 | 3200 | 3300 | 3400 | 3500
Retainer revenue (clients x avg retainer)
Ad spend markup (15% on avg $2,000 managed spend x clients)
Setup fees ($1,500 x new clients, first month each) | 0 | 3000 | 3000 | 3000 | 3000 | 6000 | 4500 | 4500 | 3000 | 4500 | 3000 | 4500 | 3000
Premium add-ons ($200/month x clients from Month 5)
Total Gross Revenue
PROFITABILITY (V2 — No Polsia Revenue Share ¦ YOUR Stripe ¦ Guarantee Model)
Gross Revenue
Total Operating Costs
Startup Costs
Net Cashflow (V2 Polsia-Augmented)
Cumulative Cashflow
Net Margin %

## Staffing Plan
LEADFLOW AI V2 — STAFFING & TIME COMMITMENT
De Villiers leads execution on almost all tasks. Marinus collaborates on strategy and key decisions. JigsawAI Initiative.
Role | Type | Start | Monthly Cost | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
De Villiers (Lead — owns execution) | Full oversight + execution | Month 0 | $0 (equity) | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 8 | 6 | 6 | 5
Marinus (Strategy Collaborator) | Monthly strategy review + ICP input | Month 1 | $0 (equity) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Polsia AI Agent | Co-pilot (NOT infrastructure) | Month 1 | $49/mo flat | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot | Co-pilot
Virtual Assistant #1 | Part-time Contractor | Month 4 | $800-$1,200 | 0 | 0 | 0 | 20 | 20 | 20 | 25 | 25 | 30 | 30 | 30 | 30
Virtual Assistant #2 | Part-time/Full-time | Month 9 | $1,200-$2,000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 25 | 30
BD / Sales (Commission) | Commission-based | Month 11 | $2,000+10% rev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20
KEY DIFFERENCES — V2 vs V1 PLAN
✓ V2 ownership: De Villiers owns almost all steps. Marinus reviews strategy monthly (ICPs, guarantee levels, portfolio direction).
✓ Months 1-3: +3-5 hours/week for human approval gates (De Villiers reviews all Polsia output before any client deployment).
✓ Months 4+: Approval gates faster as V2 playbooks are proven. New clients use approved templates with vertical-specific customisation.
✓ Polsia role: 'Drafts everything for De Villiers' approval' — not 'runs everything'. Quality control remains with De Villiers at all times.
✓ VAs trained on YOUR tools (Instantly, HubSpot, Expandi) — independent of Polsia interface for daily operations.
✓ Guarantee tracking: De Villiers monitors per-client meeting delivery weekly. Early intervention before guarantee payout triggers.
⚠ If Polsia unavailable: add 8-15 hrs/week manual work (content, analysis, sequence drafting). Claude API as fallback AI drafting tool.

## Scenario Summary
LEADFLOW AI V2 — THREE-SCENARIO FINANCIAL SUMMARY
Conservative ¦ Base Case ¦ Aggressive ¦ All scenarios use Polsia-Augmented architecture ¦ De Villiers (Lead) ¦ March 2026
| Month 0 (Setup) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | TOTAL
SCENARIO: CONSERVATIVE — Slow Network Activation, Long Sales Cycle
Assumptions: 2-3 months infra ramp ¦ Avg retainer $2,500 (Launch-heavy) ¦ 8-10% churn ¦ ~14-18 clients Year-end ¦ No major network wins
Active Clients (end of month) | 0 | 0 | 1 | 2 | 3 | 5 | 7 | 9 | 11 | 12 | 14 | 16 | 18
Average Retainer ($/month) | 0 | 0 | 2500 | 2500 | 2500 | 2600 | 2700 | 2800 | 2800 | 2900 | 2900 | 3000 | 3000
Churn Rate (monthly %) | 0% | 0% | 10% | 10% | 9% | 8% | 8% | 8% | 8% | 7% | 7% | 7% | 7%
Retainer Revenue (clients × retainer)
Estimated Operating Costs (28% of revenue + fixed $1,500)
Net Cashflow
Cumulative Cashflow
SCENARIO: BASE CASE — Realistic Network Activation, Steady Growth
Assumptions: Month 1-2 network warm-up ¦ Avg retainer $3,000 (blended Launch/Growth) ¦ 5-6% churn ¦ ~22-27 clients Year-end ¦ Normal execution
Active Clients (end of month) | 0 | 2 | 4 | 6 | 8 | 12 | 15 | 18 | 20 | 23 | 25 | 27 | 27
Average Retainer ($/month) | 0 | 0 | 2500 | 2700 | 2800 | 3000 | 3000 | 3100 | 3200 | 3200 | 3300 | 3400 | 3500
Churn Rate (monthly %) | 0% | 0% | 8% | 7% | 6% | 6% | 6% | 5% | 5% | 5% | 5% | 4% | 4%
Retainer Revenue (clients × retainer)
Estimated Operating Costs (28% of revenue + fixed $1,500)
Net Cashflow
Cumulative Cashflow
SCENARIO: AGGRESSIVE — Fast Network Win, Referral Engine Fires Early
Assumptions: Early inlumiSA/JigsawAI client from Month 1 ¦ Avg retainer $3,500 (Growth-heavy) ¦ 4-5% churn ¦ 30+ clients Year-end ¦ Referrals from Month 3
Active Clients (end of month) | 0 | 3 | 6 | 9 | 12 | 16 | 19 | 22 | 24 | 27 | 29 | 30 | 30
Average Retainer ($/month) | 0 | 3000 | 3200 | 3500 | 3500 | 3500 | 3600 | 3700 | 3800 | 3900 | 4000 | 4000 | 4000
Churn Rate (monthly %) | 0% | 0% | 6% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
Retainer Revenue (clients × retainer)
Estimated Operating Costs (28% of revenue + fixed $1,500)
Net Cashflow
Cumulative Cashflow
SCENARIO COMPARISON SUMMARY
Metric | Conservative | Base Case | Aggressive
Year-end active clients | 14-18 | 22-27 | 30+ | Plan for Base, budget for Conservative
Year 1 gross revenue (est.) | ~$380K-$480K | ~$600K-$720K | ~$1.0M-$1.2M | Conservative if no network wins by Month 2
Break-even month | Month 7-8 | Month 5-6 | Month 3-4 | Year 2 target if Base Case achieved
Average retainer (Year-end) | $3,000 | $3,500 | $4,000 | Guard: don't over-discount to win early clients
Year-end MRR | $42K-$54K | $80K-$95K | $120K+ | Base Case MRR positions for strong Year 2
Key risk | Slow early pipeline | Execution pace | Guarantee delivery at scale | Monitor guarantee payout rate weekly